## Sheet1
Development
S. No. | Product Category | Supplier | API Specs? (Y/N) | Credentials? (Y/N) | Rework? | Developer's Name | SI Flow Available? | Component Sheet? | Start Date | End Date | Remarks
1 | Accommodation | Staah (switch) | Y | Y |  |  | N | N |  |  | 20/1 - No documentation available to start development
2 | Accommodation | Lido | Y | Y |  | Joe | N | N | 2017-01-23 | 2017-01-31 | 20/1 - Fresh development
3 | Accommodation | WHL | Y | Y |  | Vasudha | Y | N | 2017-01-23 | 2017-01-31 | 20/1 - Fresh development
4 | Accommodation | Tuniu | Y | Y |  | Sachin | N | N | 2017-01-23 | 2017-01-31 | 31/1 - On Hold , discussion on Channel Manager Implementation needed 25/1- Same as 23rd 24/1 - Same as 23rd 23/1 - Understanding the channel manager implementation 20/1 - Fresh development
5 | Accommodation | Ctrip | Y | Y |  | Amrita | N | N | 2017-01-23 | 2017-01-31 | 20/1 - Fresh development
6 | Accommodation | RateHawk / Ostrovok | Y | Y |  |  | N | N |  |  | 20/1 - No API docs and credentials available
7 | Accommodation | GetaBed | Y | Y |  | V2 | N | N | 2017-01-23 | 2017-01-31 | 20/1 - Fresh development
8 | Activities | Viator | Y | Y |  | Joe | Y | Y |  |  | 20/1 - CnK dependencies on cancellation service
9 | Activities | GiftXOXO/Frogo | Y | Y | Y | Sahil | Y | Y | 2017-01-20 | 2017-01-25 | 20/1 - Re-development started
10 | Activities | Sports Event 365 | Y | Y |  | Sahil | Y | Y |  |  | 20/1 - Supplier dependency on booking service
11 | Activities | Hotel Beds | Y | Y |  | Joe | Y | Y |  |  | 20/1 - Supplier dependencies on amendment service
12 | Air | Tiger Airways | Y | Y |  | Bhagyashree | N | N | 2017-01-23 | 2017-01-27 | 20/1 - Copy of Flyscoot
13 | Car Rentals | Clear Car Rental | Y | Y |  | Atul | Y | N | 2017-01-23 | 2017-01-27 | 03/02-Code development completed. Code check-in done. 31/01- Build is Completed. Need to test end to end and code checkin with sample xml. 27/01- search operation is completed. Started with booking. 25/01-Getting diff types of response base on diff travel type. does not getting response for travel type Transfer. Email sent to supplier, request for sample data 24/01-Started with search operation. Business services tested. 23/01- doc does not contain unique key i.e. API KEY which was suppose to be provided by supplier; email sent to supplier. Unable to test all are url with all posible combination of values which is in doc. 20/1 - Fresh development
14 | Car Rentals | Zoom Cars | Y | Y |  | Atul | Y | N |  | 2017-01-19 | 20/1 - Development completed; pending peer review 23/01- updated the code for validate activity which was not working in AWS, code checked in
15 | Cruise | MSC Cruise | Y | Y |  | Amrita | Y | Y |  | 2017-01-20 | 20/1 - Development complete; Interface XMLs to be checked-in
16 | Cruise | Royal Carribean | Y | Y | Y | Winston | Y | Y | 2017-01-17 | 2017-01-25 | 20/1 - Re-development in-progress
17 | Cruise | Star Cruise | Y | Y | Y | Amrita | Y | Y |  |  | 20/1 - Supplier dependencies on new fields
18 | Miscellaneous | Columbus Travel Guide | Y | Y |  | Mukul | Y | N | 2017-01-23 | 2017-01-27 | 20/1 - Fresh development
19 | Miscellaneous | Wunderground | Y | Y |  | Kishor | N | N | 2017-01-23 | 2017-01-27 | 20/1 - Fresh development
20 | Miscellaneous | Park N Fly | Y | Y |  | Shrikant G | N | N | 2017-01-23 | 2017-01-27 | 24/1 - Key is not working awaiting for supplier response 23/1 - Making Artifacts,Schemas and WSDLs 20/1 - Fresh development
21 | Packages | Cosmos and Globus | Y | Y |  | Priyana | Y | Y | 2017-01-02 | 2017-01-24 | 23/1 - Dev Completed
22 | Packages | Contiki | Y | Y |  | Venky | Y | Y |  | ?? | 20/1 - Devleopment done and bugs resolved 20/1 - What is the update on this?
23 | Packages | Insight Vacations | Y | Y |  | Venky | Y | Y |  | ?? | 20/1 - Devleopment done and bugs resolved 20/1 - What is the update on this?
24 | Packages | Trafalgar | Y | Y |  | Venky | Y | Y |  | ?? | 20/1 - Devleopment done and bugs resolved 20/1 - What is the update on this?
25 | Packages | The Traveller | Y | Y |  | Priyana | Y | Y |  |  | 20/1 - Dependency on supplier
26 | Payment Gateway | Asia Pay | Y | Y
27 | Payment Gateway | HDFC Bank | Y | Y
28 | Rail | Silverrail | Y | Y |  | Kanif/Venky | Y | N | 2017-01-23 | 2017-02-03 | 23/1 - Supplier on hold due to contractual problems from cnk 20/1 - Fresh development
29 | Rail | IRCTC | Y | Y |  | Sahil/Bhagyashree | Y | Y | 2017-01-23 | 2017-02-08 | 20/1 - Fresh development
30 | Transfers | Holiday Taxi | Y | Y |  | Sachin | N | N | 2017-01-23 | 2017-01-27 | 03/02- All the 4 CS developed and code checked in 02/02- Search,NewBooking and GetBooking CS completed, CancelCS Response mapping pending, will be moving to AWS tomorrow 31/1- Search CS Completed, Create,Get and Cancel Booking build completed, Few Mappings and Testing pending 25/1 - Search CS build complete, issue with booking API, no reply from supplier 24/1 - Search CS build in progress, issue with booking API, sent a mail to supplier 23/1 - Credentials not working, sent a mail to the supplier 20/1 - Fresh development
31 | Insurance | Covermore Insurance | Y | Y | Y | Venky | Y | Y | ?? | ?? | 24/1 - Development in progress 20/1 - What is the update on this?